## Sheet1
Buccaneer Project Calendar |  | NOVEMBER | [19 empty] | DECEMBER | [19 empty] | JANUARY
|  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
PROJECT | RESPONSIBLE | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25
Logo Kick off | Brooke/James
Logo Initial design (black and white) | Brooke/James
Presentation of initial logo design | Brooke/James
Logo design v2 (color) | Brooke/James
Presentation of final logo design | Brooke/James
Finalized logo approved | ALL
Delivery of final logo files | James
Sitemap | Brooke
Sitemap changes/sign off | Buccaneer
Feedback on sites - what you like/dislike about sample sites | Buccaneer
Wireframe mockups | Brooke
Feedback/Sign off on wireframe mockups | Buccaneer
Any tweaks to wireframe mockups | Brooke
Designer Brief | Brooke
Content template | Brooke
Design first draft (V1) (homepage) | HopCreative
First draft of content - based on content template | Brooke/Buccaneer
Design feedback to HopCreative (V1 based on homepage) | Brooke/Buccaneer
Design V2 based on V1 feedback (homepage, landing) | HopCreative
Additional changes/finalize content | Brooke/Buccaneer
Any necessary second design draft feedback to HopCreative | Brooke/Buccaneer
Finalize design | HopCreative
Sign off on design | Brooke/Buccaneer
Domain setup | Mike
Initial build/implement content | Mike
Test site review/Q&A (V1) | Brooke
Developer revisions | Mike
Test site review/Q&A (V2) | Brooke
Developer final revisions | Mike
Buccaneer website peek/final feedback | Buccaneer
Go Live | Mike
Wordpress Training | Brooke